## Table1
Title | ID | Owner | Status | Est. Hours | To Do | Backlog | Sprint | Planning Level
access | TK-2821053 | Ari Sherman | In Progress | 2 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
access | TK-2627473 | Ari Sherman | In Progress | 1 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Access | TK-2821064 | Jonathan Trodglen | In Progress | 1 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Access | TK-2791576 | Jonathan Trodglen | In Progress | 1 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Ad Hoc Reports | TK-2426924 | Raheel Aidrus | In Progress | 2 | 2 | Data Ingests into UAP: Carriers After Last Truck Departure - AdHoc Reports | Sprint 270 | UAP-IV-9443
Add timeit | TK-2821163 | Gurpreet Kaur | In Progress | 16 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443
Add timeit | TK-2808249 | Gurpreet Kaur | In Progress | 1 | 1 | Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 270 | UAP-IV-9443
Ad-hoc | TK-2821051 | Ari Sherman | In Progress | 8 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Ad-hoc | TK-2627471 | Ari Sherman | In Progress | 22 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Ad-hoc | TK-2821056 | Yella Vanga | In Progress | 4 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Ad-hoc | TK-2641096 | Yella Vanga | In Progress | 2 | 2 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Ad-hoc | TK-2821059 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Ad-hoc | TK-2674746 | Dudley Pratt | In Progress | 1 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Ad-Hoc | TK-2821062 | Jonathan Trodglen | In Progress | 46 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Ad-Hoc | TK-2791574 | Jonathan Trodglen | In Progress | 37.5 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Adhoc/Miscellaneous Work | TK-2821060 | Christine Trang Mai | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Adhoc/Miscellaneous Work | TK-2697274 | Christine Trang Mai | In Progress | 11 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Admin tasks | TK-2618428 | Vandana Singh | In Progress | 2 | 2 | Postal Wiki: GenAI - Postal Wiki Review App | Sprint 270 | UAP-IV-9443
Agent Iteration Log Implementation | TK-2694447 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
AI Curator Code Updates | TK-2821168 | Gurpreet Kaur | Completed | 16 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
AI Sandbox Test Coverage | TK-2725844 | Tyler Russin-Mirabito | In Progress | 1 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Analysis | TK-2821109 | Margaret Albiniak | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443
Analysis | TK-2555146 | Margaret Albiniak | In Progress | 5.5 | 1 | Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443
App code understanding and enhancements | TK-2618427 | Vandana Singh | In Progress | 5 | 5 | Postal Wiki: GenAI - Postal Wiki Review App | Sprint 270 | UAP-IV-9443
App service Easy Auth/Okta config updates to filter down groups sent in claims | TK-2829641 | Thomas Petty | Completed | 4.5 | 0 | CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443
Architecture Review and Assessment | TK-2684770 | Rumeel Kazi | In Progress | 32 | 32 | CDAO Architecture: Architecture Review and Assessments - EDW PPR Migration to UAP Assessment | Sprint 270 | UAP-IV-9443
Azure Data Factory Configuration | TK-2821088 | Henry Brandenburg | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
Azure Data Factory Configuration | TK-2561607 | Henry Brandenburg | In Progress | 10 | 10 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
Azure Function App support | TK-2821098 | Ravi Bhupatiraju | In Progress | 7 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
Azure Function App support | TK-2817619 | Ravi Bhupatiraju | In Progress | 8 | 8 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
Azure Production Deployment | TK-2732320 | Tyler Russin-Mirabito | In Progress | 1 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Build frameworks to ingest WebEOR data into bronze and silver layers | TK-2821196 | Tracey Jacoby | In Progress | 72 | 0 | Copy Of UAP - ING Data Ingests - Ingest WebEOR | Sprint 269 | UAP-IV-9443
Build frameworks to ingest WebEOR data into bronze and silver layers | TK-2806977 | Tracey Jacoby | In Progress | 1 | 1 | UAP - ING Data Ingests - Ingest WebEOR | Sprint 270 | UAP-IV-9443
Build Fraud unpaid PPI mail barcode Daily | TK-2776235 | Lucky Winebarger | In Progress | 1 | 1 | Data Ingests into UAP - Fraud Dataset for EDW | Sprint 270 | UAP-IV-9443
CDAO GenAI Data SME and Lead (incl Postal Wiki, AI Sandbox, Conversational Mobile App) | TK-2650855 | Kaelynn Koch | In Progress | 1 | 1 | CDAO GenAI Architecture Support | Sprint 270 | UAP-IV-9443
CDAO General Business Support | TK-2821017 | Kaelynn Koch | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
CDAO General Business Support | TK-2604241 | Kaelynn Koch | In Progress | 1 | 1 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
CDAO General Support Work | TK-2821013 | Margaret Albiniak | In Progress | 8 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
CDAO General Support Work | TK-2234933 | Margaret Albiniak | In Progress | 8 | 1 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
CDAO Postal Wiki: Clone code and setup app | TK-2618429 | Vandana Singh | In Progress | 2 | 2 | Postal Wiki: GenAI - Postal Wiki App | Sprint 270 | UAP-IV-9443
CDAO Postal Wiki: Get development ready | TK-2625894 | Gurpreet Kaur | In Progress | 4 | 4 | Postal Wiki: GenAI - Postal Wiki App | Sprint 270 | UAP-IV-9443
CDAO Postal Wiki: Lead and Data SME Support | TK-2618422 | Kaelynn Koch | In Progress | 1 | 1 | Postal Wiki: GenAI - Postal Wiki App | Sprint 270 | UAP-IV-9443
CDAO Postal Wiki: Review solution diagram and list tasks | TK-2625865 | Gurpreet Kaur | In Progress | 8 | 8 | Postal Wiki: GenAI - Postal Wiki App | Sprint 270 | UAP-IV-9443
CDAO Power BI Knowledge Share | TK-2821032 | Margaret Albiniak | In Progress | 1 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443
CDAO Power BI Knowledge Share | TK-2803057 | Margaret Albiniak | In Progress | 2 | 1 | CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443
CDAO/DAS General Business Support | TK-2821011 | Denetta Eager | In Progress | 27.5 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
CDAO/DAS General Business Support | TK-2145065 | Denetta Eager | In Progress | 70 | 30.5 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
CDAO: Platform Support: Access Support | TK-2821042 | Christine Trang Mai | In Progress | 8 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 269 | UAP-IV-9443
CDAO: Platform Support: Access Support | TK-2813837 | Christine Trang Mai | In Progress | 10 | 1 | CDAO: Platform Support: Access Support | Sprint 270 | UAP-IV-9443
CDAO: Platform Support: Access Support | TK-2821043 | Dudley Pratt | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 269 | UAP-IV-9443
CDAO: Platform Support: Access Support | TK-2814488 | Dudley Pratt | In Progress | 1 | 1 | CDAO: Platform Support: Access Support | Sprint 270 | UAP-IV-9443
CDAO: Platform Support: Access Support | TK-2828432 | Ahsan Hashmi | In Progress | 10 | 1 | CDAO: Platform Support: Access Support | Sprint 270 | UAP-IV-9443
CDAO: Platform Support: Administrative Support | TK-2821066 | Christine Trang Mai | In Progress | 2 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
CDAO: Platform Support: Administrative Support | TK-2813341 | Christine Trang Mai | In Progress | 7 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
CDAO: Platform Support: Cloud Services Support | TK-2821662 | Christine Trang Mai | In Progress | 7 | 1 | CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443
CDAO: Platform Support: Deployment Support | TK-2821083 | Christine Trang Mai | In Progress | 1 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
CDAO: Platform Support: Deployment Support | TK-2813484 | Christine Trang Mai | In Progress | 4 | 1 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
CDAO: Platform Support: Infrastructure Support | TK-2821093 | Christine Trang Mai | In Progress | 14 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
CDAO: Platform Support: Infrastructure Support | TK-2813481 | Christine Trang Mai | In Progress | 33 | 1 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
CDAO: Platform Support: Infrastructure Support | TK-2821094 | Dudley Pratt | In Progress | 4 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
CDAO: Platform Support: Infrastructure Support | TK-2814492 | Dudley Pratt | In Progress | 1 | 1 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
CDAO-Platform Support: Security | TK-2821102 | Christine Trang Mai | In Progress | 6 | 0 | Copy Of CDAO: Platform Support: Security | Sprint 269 | UAP-IV-9443
CDAO-Platform Support: Security | TK-2813477 | Christine Trang Mai | In Progress | 10 | 1 | CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443
change Domain-column_name-catalog pair | TK-2801358 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.2 | Sprint 269 | UAP-IV-9443
CIO Data Strategy Support and Tech Chat | TK-2821050 | Rumeel Kazi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
CIO Data Strategy Support and Tech Chat | TK-2548919 | Rumeel Kazi | In Progress | 32 | 32 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Cloud Access Support | TK-2821041 | Yella Vanga | In Progress | 11 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 269 | UAP-IV-9443
Cloud Access Support | TK-2647089 | Yella Vanga | In Progress | 16 | 4 | CDAO: Platform Support: Access Support | Sprint 270 | UAP-IV-9443
Cloud Cost Meeting | TK-2821021 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
Cloud Cost Meeting | TK-2762787 | Jiang Jing Guang | In Progress | 39.5 | 39.5 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
Cloud Cost Reporting | TK-2821105 | Denetta Eager | In Progress | 18 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443
Cloud Cost Reporting | TK-2435259 | Denetta Eager | In Progress | 20 | 3 | Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443
Cloud Costing Analysis/Monitoring/Reporting | TK-2821103 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443
Cloud Costing Analysis/Monitoring/Reporting | TK-2414177 | Peermohamed Kajakamaludeen | In Progress | 1 | 1 | Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443
Cloud Service Support | TK-2821075 | Yella Vanga | In Progress | 32 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 269 | UAP-IV-9443
Cloud Service Support | TK-2790529 | Yella Vanga | In Progress | 24 | 4 | CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443
Cloud Subscription Administrative Work | TK-2821104 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443
Cloud Subscription Administrative Work | TK-2414187 | Peermohamed Kajakamaludeen | In Progress | 1 | 1 | Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443
Cluster Policies | TK-2821087 | Ravi Bhupatiraju | In Progress | 20 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
Cluster Policies | TK-2382330 | Ravi Bhupatiraju | In Progress | 40 | 20 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
Code development and testing | TK-2741355 | Gener Mercado | In Progress | 72 | 1 | Data Ingests into UAP - Facility Golden Record to UAP | Sprint 270 | UAP-IV-9443
Coding | TK-2821120 | Kai Lebert | Completed | 24 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 269 | UAP-IV-9443
Column description generation for all nmat tables in silver schema in salprod | TK-2683566 | Vandana Singh | In Progress | 1 | 1 | Postal Wiki: GenAI - AI Enabled Sales Metadata Generation | Sprint 270 | UAP-IV-9443
Comment Generation: Create compute, set schedule | TK-2788711 | Gurpreet Kaur | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443
Comment Generation: Flip flags to 'N' if 'Y' in ai_curator_config at the end of job run | TK-2788719 | Gurpreet Kaur |  | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443
Comment Generation: Job delay alerts | TK-2788688 | Gurpreet Kaur | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443
Comment Generation: Switch edh context to pandas df | TK-2788715 | Gurpreet Kaur | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443
Comment Generation: Update the 'DEFAULT_TABLE_FILTER' name to 'UNALLOWED_TABLE' in ai_curator_configs | TK-2788749 | Gurpreet Kaur |  | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443
Cost Management | TK-2821074 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 269 | UAP-IV-9443
Cost Management | TK-2674747 | Dudley Pratt | In Progress | 3 | 3 | CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443
create and populate 3 tables for TOPS lookups | TK-2821151 | Walter Tallent |  | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
create and populate 3 tables for TOPS lookups | TK-2735376 | Walter Tallent |  | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Create class of metadata generation notebook | TK-2694937 | Vandana Singh | In Progress | 7 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443
Create different DMLs for table clean-up, PROD runs, including all domains for salprod | TK-2821175 | Vandana Singh | Completed | 6 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
create ingests for new tables from eFMS database | TK-2821152 | Walter Tallent |  | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
create ingests for new tables from eFMS database | TK-2735390 | Walter Tallent |  | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Create New Job for Databricks Cluster Dependency Scanning | TK-2829643 | Thomas Petty | Completed | 5 | 0 | CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443
Create/Update Cluster Policies | TK-2834517 | Ahsan Hashmi | In Progress | 12 | 1 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
DAS All Team Meeting | TK-2821015 | Laheeb Alsarraf |  | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
DAS All Team Meeting | TK-2513755 | Laheeb Alsarraf |  | 11 | 11 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
DAS Deployment Support | TK-2821085 | Ravi Bhupatiraju | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
DAS Deployment Support | TK-2817585 | Ravi Bhupatiraju | In Progress | 40 | 20 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
DAS Platform Support | TK-2821090 | Henry Brandenburg |  | 33.5 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
DAS Platform Support | TK-2562975 | Henry Brandenburg |  | 1 | 1 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
Data Analysis & Team Tracker changes updates | TK-2821125 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 269 | UAP-IV-9443
Data Analysis & Team Tracker changes updates | TK-2743207 | Chandrasekhar Malapati | In Progress | 2 | 2 | Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443
Data SME & Functional Architecture | TK-2666323 | Kaelynn Koch | In Progress | 1 | 1 | GenAI: Data Rationalization Architecture | Sprint 270 | UAP-IV-9443
Databricks Collaboration | TK-2821065 | Denetta Eager | In Progress | 2.5 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Databricks Lunch & Learn Series | TK-2821027 | Margaret Albiniak | Completed | 0 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443
Databricks Tagging Analysis | TK-2821106 | Denetta Eager | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443
Databricks Tagging Analysis | TK-2522143 | Denetta Eager | In Progress | 6.5 | 4 | Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443
Databricks Tagging for Cost Analysis | TK-2821107 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443
Databricks Tagging for Cost Analysis | TK-2537319 | Peermohamed Kajakamaludeen | In Progress | 1 | 1 | Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443
Databricks Tagging support | TK-2829645 | Thomas Petty | Completed | 0.5 | 0 | CDAO: Platform Support: Reporting Platform Support | Sprint 270 | UAP-IV-9443
Databricks Worfklow / Job Support | TK-2821080 | Denetta Eager | In Progress | 5.5 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
Databricks Worfklow / Job Support | TK-2775781 | Denetta Eager | In Progress | 3 | 3 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
DDL and DML for ai_curator_acronym | TK-2821172 | Vandana Singh | Completed | 0 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
DDL and DML for ai_curator_glossary | TK-2821171 | Vandana Singh | Completed | 5 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
Deployment Support | TK-2821079 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
Deployment Support | TK-2641108 | Yella Vanga | In Progress | 2 | 2 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
deployments | TK-2821078 | Ari Sherman | In Progress | 6 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
deployments | TK-2627465 | Ari Sherman | In Progress | 13 | 1 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
Deployments | TK-2821081 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
Deployments | TK-2777338 | Dudley Pratt | In Progress | 1 | 1 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
Deployments | TK-2821082 | Jonathan Trodglen | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
Deployments | TK-2791572 | Jonathan Trodglen | In Progress | 2.5 | 1 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
Design and development | TK-2821123 | Gener Mercado | In Progress | 55 | 0 | Copy Of Data Ingests into UAP - Facility Golden Record to UAP | Sprint 269 | UAP-IV-9443
Design/Model | TK-2517189 | Kranthi Miryala | In Progress | 2 | 2 | Cloud Administration: Role Based Access and Security: Immuta POC - General Product, Project, and Business Support | Sprint 270 | UAP-IV-9443
Develop strategy to consolidate tasks and reduce number of agents | TK-2631968 | Gurpreet Kaur | In Progress | 8 | 8 | Postal Wiki: GenAI - Postal Wiki App | Sprint 270 | UAP-IV-9443
Development | TK-2821113 | Michael Li |  | 39 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443
Development | TK-2289393 | Michael Li |  | 40 | 32 | Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443
Development | TK-2821114 | Raheel Aidrus | In Progress | 16 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443
Development | TK-2330194 | Raheel Aidrus | In Progress | 16 | 4 | Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443
Development | TK-2443641 | Raheel Aidrus | In Progress | 4 | 4 | Data Ingests into UAP: Carriers After Last Truck Departure - CTE Data onto Kafka Topic | Sprint 270 | UAP-IV-9443
Development | TK-2618011 | Michael Li | In Progress | 1 | 1 | Data Ingests into UAP: Carriers After Last Truck Departure - CTE Data onto Kafka Topic | Sprint 270 | UAP-IV-9443
Development | TK-2618058 | Michael Li |  | 1 | 1 | Data Ingests into UAP: Carriers After Last Truck Departure - AdHoc Reports | Sprint 270 | UAP-IV-9443
Development | TK-2821118 | Andrew Toy | In Progress | 0 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443
Development | TK-2669604 | Andrew Toy | In Progress | 1 | 1 | Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443
Development | TK-2821111 | Michael Li |  | 0 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 269 | UAP-IV-9443
Development | TK-2748229 | Michael Li |  | 32 | 32 | Conversation Chat: DCS/MPE Integration | Sprint 270 | UAP-IV-9443
Development | TK-2821112 | Raheel Aidrus | In Progress | 2 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 269 | UAP-IV-9443
Development | TK-2748230 | Raheel Aidrus | In Progress | 1 | 1 | Conversation Chat: DCS/MPE Integration | Sprint 270 | UAP-IV-9443
development | TK-2821037 | Steven Stewart | In Progress | 0 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - Data: Create Workflows/Tables Needed for Facility Level Pure Productive | Sprint 269 | UAP-IV-9443
development | TK-2817932 | Steven Stewart | In Progress | 40 | 40 | CDAO: Network Dashboard - Enhancements - Data: Create Workflows/Tables Needed for Facility Level Pure Productive | Sprint 270 | UAP-IV-9443
Development and Deployment | TK-2821135 | Raheel Aidrus | In Progress | 8 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FEA Facility Data API | Sprint 269 | UAP-IV-9443
Development and Deployment | TK-2789974 | Raheel Aidrus | In Progress | 8 | 4 | Data Ingests into UAP: DAS API Development - FEA Facility Data API | Sprint 270 | UAP-IV-9443
Development and Deployment | TK-2821133 | Raheel Aidrus | In Progress | 8 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FAST API | Sprint 269 | UAP-IV-9443
Development and Deployment | TK-2789975 | Raheel Aidrus | In Progress | 10 | 4 | Data Ingests into UAP: DAS API Development - FAST API | Sprint 270 | UAP-IV-9443
Development and Deployment of API for File Upload | TK-2821139 | Raheel Aidrus | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
Development and Deployment of API for File Upload | TK-2576627 | Raheel Aidrus | In Progress | 8 | 8 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Development and Meetings | TK-2821116 | Bryan Stetson | In Progress | 0 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443
Development and Meetings | TK-2538062 | Bryan Stetson | In Progress | 11 | 1 | Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443
Development and Testing | TK-2821136 | Andrew Toy | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FEA Facility Data API | Sprint 269 | UAP-IV-9443
Development and Testing | TK-2789979 | Andrew Toy | In Progress | 8 | 1 | Data Ingests into UAP: DAS API Development - FEA Facility Data API | Sprint 270 | UAP-IV-9443
Development and Testing | TK-2821134 | Andrew Toy | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FAST API | Sprint 269 | UAP-IV-9443
Development and Testing | TK-2789980 | Andrew Toy | In Progress | 12.5 | 1 | Data Ingests into UAP: DAS API Development - FAST API | Sprint 270 | UAP-IV-9443
Developments and Updates | TK-2237462 | Ralinkae Kane-Jackson | In Progress | 1 | 1 | CDAO: Network Dashboard - Supporting Documentation and Observability - Data Dictionaries | Sprint 270 | UAP-IV-9443
DML for ai_generated_comment table | TK-2820410 | Vandana Singh | Completed | 3 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443
DML for fixing existing run_id | TK-2821187 | Gurpreet Kaur | Completed | 4 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443
Document tasks and functionalities of each agent | TK-2632055 | Gurpreet Kaur | In Progress | 4 | 4 | Postal Wiki: GenAI - Postal Wiki App | Sprint 270 | UAP-IV-9443
DSG General SME Support | TK-2673636 | Kaelynn Koch | In Progress | 2 | 2 | CDAO GenAI Architecture Support | Sprint 270 | UAP-IV-9443
EDH Deployment Support | TK-2821084 | Ahsan Hashmi | In Progress | 24 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
EDH Deployment Support | TK-2815775 | Ahsan Hashmi | In Progress | 16 | 1 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
EDH PROD Support | TK-2821099 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 269 | UAP-IV-9443
EDH PROD Support | TK-2777337 | Dudley Pratt | In Progress | 1 | 1 | CDAO: Platform Support: Production Support | Sprint 270 | UAP-IV-9443
EDH view, ai_comments, innovation squad assets comparison | TK-2821178 | Vandana Singh | Completed | 3 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
Efms TT1689 Additional tables | TK-2821147 | Archana Wathore | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
Efms TT1689 Additional tables | TK-2731164 | Archana Wathore | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
EIRs for UAP Solution Architecture Support | TK-2821049 | Rumeel Kazi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
EIRs for UAP Solution Architecture Support | TK-2548917 | Rumeel Kazi | In Progress | 32 | 32 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Email Validation Workflow | TK-2756329 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443
eModeMatrix - DMCR & TT1605 model changes analysis | TK-2821140 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
eModeMatrix - DMCR & TT1605 model changes analysis | TK-2588115 | Chandrasekhar Malapati | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Evaluate TOPS and NDLL data for ingestion | TK-2821138 | Joseph Martinez | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
Evaluate TOPS and NDLL data for ingestion | TK-2513237 | Joseph Martinez | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Extract EEB Data for Validation in EDW | TK-2764059 | Robert Bradsher | In Progress | 1 | 1 | Data Ingests into UAP - EDW PPR Migration to UAP | Sprint 270 | UAP-IV-9443
FAST - DS, OE files Data Ingest for new 3 column changes | TK-2821121 | Chandrasekhar Malapati | In Progress | 3 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 269 | UAP-IV-9443
FAST - DS, OE files Data Ingest for new 3 column changes | TK-2783562 | Chandrasekhar Malapati | In Progress | 6 | 2 | Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 270 | UAP-IV-9443
FAST Dev Team Support | TK-2834847 | Kai Lebert | In Progress | 20 | 5 | Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 270 | UAP-IV-9443
FAST Environment Configuration | TK-2630390 | Henry Brandenburg | In Progress | 0.5 | 0.5 | Data Ingests - Package Payment Scoring PPS EIR 9444: General Business Support | Sprint 270 | UAP-IV-9443
FDB Feed for UAP using FDB Web Services | TK-2721301 | Robert Bradsher | In Progress | 1 | 1 | Data Ingests into UAP - FEA to UAP: FDB Data Feed | Sprint 270 | UAP-IV-9443
FEA- Ingest Unit, system Testing | TK-2829399 | Chandrasekhar Malapati | In Progress | 40 | 24 | Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443
FEA-AMS Feed Development | TK-2821124 | Chandrasekhar Malapati | In Progress | 13 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 269 | UAP-IV-9443
FEA-AMS Feed Development | TK-2733282 | Chandrasekhar Malapati | In Progress | 2 | 2 | Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443
FEA-EFMS Development | TK-2821126 | Chandrasekhar Malapati | In Progress | 16 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 269 | UAP-IV-9443
FEA-EFMS Development | TK-2757017 | Chandrasekhar Malapati | In Progress | 40 | 16 | Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443
FEA-FNCM Feed Analysis | TK-2821127 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 269 | UAP-IV-9443
FEA-FNCM Feed Analysis | TK-2757018 | Chandrasekhar Malapati | In Progress | 4 | 4 | Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443
Functional architect and data sme | TK-2694933 | Kaelynn Koch | In Progress | 1 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Functional architecture and data sme | TK-2694932 | Kaelynn Koch | In Progress | 1 | 1 | GenAI: CDAO Service Root Cause Analytics Architecture | Sprint 270 | UAP-IV-9443
Functional Support & Meetings | TK-2267566 | Charles Gorelik | In Progress | 8 | 8 | CDAO: Network Dashboard - Supporting Documentation and Observability - Data Dictionaries | Sprint 270 | UAP-IV-9443
General Meeting and Solutions | TK-2821024 | Jiang Jing Guang | In Progress | 2.5 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
General Meeting and Solutions | TK-2810050 | Jiang Jing Guang | In Progress | 97.5 | 97.5 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
generate comments and test SPM tables in lower environment | TK-2807033 | Vandana Singh | In Progress | 4 | 0 | Postal Wiki: AI Curator Release 2.2 | Sprint 269 | UAP-IV-9443
GitHub Copilot | TK-2821022 | Kai Lebert | In Progress | 4 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
GitHub Copilot | TK-2777258 | Kai Lebert | In Progress | 10 | 1 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
GitHub CoPilot Onboarding and Training / Prompt Engineering | TK-2821029 | Michael Tran | In Progress | 2 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443
GitHub CoPilot Onboarding and Training / Prompt Engineering | TK-2820149 | Michael Tran | In Progress | 8 | 8 | CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443
GitHub CoPilot Onboarding and Training / Prompt Engineering | TK-2821030 | Denetta Eager | In Progress | 0.5 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443
GitHub CoPilot Onboarding and Training / Prompt Engineering | TK-2790906 | Denetta Eager | In Progress | 8.5 | 8.5 | CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443
Graph Creation Tool | TK-2749769 | Tyler Russin-Mirabito | In Progress | 40 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
HR Modernization Meetings | TK-2821020 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
HR Modernization Meetings | TK-2712978 | Jiang Jing Guang | In Progress | 38.5 | 38.5 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
Identify duplicate functionality | TK-2631966 | Gurpreet Kaur | In Progress | 4 | 4 | Postal Wiki: GenAI - Postal Wiki App | Sprint 270 | UAP-IV-9443
Immuta POC | TK-2501627 | Thomas Petty | In Progress | 0 | 0 | Cloud Administration: Role Based Access and Security: Immuta POC - General Product, Project, and Business Support | Sprint 270 | UAP-IV-9443
Immuta POC Support | TK-2648769 | Joseph Martinez | In Progress | 1 | 1 | Cloud Administration: Role Based Access and Security: Immuta POC - General Product, Project, and Business Support | Sprint 270 | UAP-IV-9443
Implement Logs in SPM code | TK-2669712 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
import data from edw (PPS) | TK-2821145 | Walter Tallent | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
import data from edw (PPS) | TK-2681023 | Walter Tallent | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Improve logging | TK-2821164 | Gurpreet Kaur | Completed | 4 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443
Improvements to SQL RAG Feature | TK-2821117 | Bryan Stetson | In Progress | 0 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443
Improvements to SQL RAG Feature | TK-2614037 | Bryan Stetson | In Progress | 11 | 1 | Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443
Infrastructure Support | TK-2821091 | Yella Vanga | In Progress | 31 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
Infrastructure Support | TK-2790548 | Yella Vanga | In Progress | 30 | 10 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
ingest nassweb aft file into databricks | TK-2821129 | Walter Tallent |  | 23 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: NASSWEB Data Feed | Sprint 269 | UAP-IV-9443
ingest nassweb aft file into databricks | TK-2802830 | Walter Tallent |  | 1 | 1 | Data Ingests into UAP - FEA to UAP: NASSWEB Data Feed | Sprint 270 | UAP-IV-9443
ingest properties kafka topic | TK-2821197 | Walter Tallent |  | 12 | 0 | Copy Of UAP-ING Data Ingests - Ingeset IPME data for Properties | Sprint 269 | UAP-IV-9443
ingest properties kafka topic | TK-2803788 | Walter Tallent |  | 30 | 22 | UAP-ING Data Ingests - Ingeset IPME data for Properties | Sprint 270 | UAP-IV-9443
Integration | TK-2821054 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Integration | TK-2640983 | Yella Vanga | In Progress | 2 | 2 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Integration Help for Client Apps | TK-2821115 | Raheel Aidrus | In Progress | 6 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443
Integration Help for Client Apps | TK-2460712 | Raheel Aidrus | In Progress | 12 | 3 | Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443
Investigate and fix domain_prompt_config table in DEV | TK-2821174 | Vandana Singh | Completed | 2 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
Investigate and update edh_bronze.metadata_asset_attribute_description table in SIT | TK-2820411 | Vandana Singh | Completed | 5.5 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443
Investigate data glossary issue in SIT | TK-2821173 | Vandana Singh | Completed | 2 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
Kafka EEB setup | TK-2821014 | Ravi Bhupatiraju |  | 20 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
Kafka EEB setup | TK-2398458 | Ravi Bhupatiraju |  | 60 | 20 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
Kai - OOO | TK-2821035 | Kai Lebert | Completed | 7 | 0 | Copy Of CDAO PTO - OOO | Sprint 269 | UAP-IV-9443
Kai Lebert | TK-2834852 | Kai Lebert | Completed | 12 | 0 | CDAO PTO - OOO | Sprint 270 | UAP-IV-9443
make changes to TOPS schema | TK-2821146 | Walter Tallent |  | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
make changes to TOPS schema | TK-2707960 | Walter Tallent |  | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Meetings | TK-2821108 | Margaret Albiniak | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443
Meetings | TK-2555145 | Margaret Albiniak | In Progress | 1 | 1 | Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443
Meetings | TK-2821110 | Bryan Stetson |  | 1 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 269 | UAP-IV-9443
Meetings | TK-2748228 | Bryan Stetson |  | 4 | 1 | Conversation Chat: DCS/MPE Integration | Sprint 270 | UAP-IV-9443
Meetings | TK-2833384 | Margaret Albiniak | In Progress | 2 | 1 | UAP-ING Data Ingests - General Project, Program, Business Support | Sprint 270 | UAP-IV-9443
Meetings (Team 06 Dev & Infrastructure) | TK-2821016 | Kai Lebert | In Progress | 11 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
Meetings (Team 06 Dev & Infrastructure) | TK-2562879 | Kai Lebert | In Progress | 6 | 1 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
meetings, research initial coding of efms ingest | TK-2821142 | Walter Tallent |  | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
meetings, research initial coding of efms ingest | TK-2604232 | Walter Tallent |  | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Meetings/Functional Support/Investigations | TK-2821039 | Charles Gorelik | In Progress | 33.5 | 0 | Copy Of CDAO: Network Dashboard - Functional and Business Support | Sprint 269 | UAP-IV-9443
Meetings/Functional Support/Investigations | TK-2576808 | Charles Gorelik | In Progress | 40 | 26.5 | CDAO: Network Dashboard - Functional and Business Support | Sprint 270 | UAP-IV-9443
Metadata File Upload App: Set up database | TK-2675244 | Gurpreet Kaur |  | 8 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Metadata File Upload App: Set up Microsoft OAuth | TK-2675246 | Gurpreet Kaur |  | 24 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Metadata File Upload App: Set up Routes | TK-2675197 | Gurpreet Kaur |  | 40 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Metadata File Upload App: Start application | TK-2675196 | Gurpreet Kaur |  | 8 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Network Analytical Dashboard | TK-2821040 | Kevin Nerio | Completed | 80 | 0 | Copy Of CDAO: Network Dashboard - Functional and Business Support | Sprint 269 | UAP-IV-9443
New appointment_dtm column | TK-2834840 | Kai Lebert | In Progress | 40 | 10 | Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 270 | UAP-IV-9443
New Task | TK-2821188 | Gurpreet Kaur | Completed | 4 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443
Palantir Support | TK-2821067 | Dudley Pratt | In Progress | 5 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Palantir Support | TK-2815347 | Dudley Pratt | In Progress | 25 | 10 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Planning, Meetings, Architecture, Sample Files | TK-2821119 | Kai Lebert | Completed | 2 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 269 | UAP-IV-9443
Platform Support Team Meetings | TK-2821061 | Denetta Eager | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Platform Support Team Meetings | TK-2769253 | Denetta Eager | In Progress | 4 | 2 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
PPS Ingest Additional work - Project Management | TK-2792552 | Peermohamed Kajakamaludeen | In Progress | 1 | 1 | Data Ingests - Package Payment Scoring PPS EIR 9444: General Business Support | Sprint 270 | UAP-IV-9443
Production Support | TK-2821100 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 269 | UAP-IV-9443
Production Support | TK-2790549 | Yella Vanga | In Progress | 4 | 4 | CDAO: Platform Support: Production Support | Sprint 270 | UAP-IV-9443
Production Support | TK-2834516 | Ahsan Hashmi | In Progress | 8 | 1 | CDAO: Platform Support: Production Support | Sprint 270 | UAP-IV-9443
Production Support DAS and FAST | TK-2821101 | Ravi Bhupatiraju | In Progress | 10 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 269 | UAP-IV-9443
Production Support DAS and FAST | TK-2817620 | Ravi Bhupatiraju | In Progress | 20 | 20 | CDAO: Platform Support: Production Support | Sprint 270 | UAP-IV-9443
Project Support | TK-2749952 | Sonya Einhorn | In Progress | 1 | 1 | Enterprise Data Hub - General Project, Program, Business Support | Sprint 270 | UAP-IV-9443
Prompt and code updates | TK-2694941 | Vandana Singh | In Progress | 8 | 8 | Postal Wiki: GenAI - AI Enabled Sales Metadata Generation | Sprint 270 | UAP-IV-9443
Prototype 1.0 creation | TK-2666326 | Vandana Singh | In Progress | 12 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443
Push/Pull data daily to EDW | TK-2776238 | Lucky Winebarger | In Progress | 1 | 1 | Data Ingests into UAP - Fraud Dataset for EDW | Sprint 270 | UAP-IV-9443
QLIK Connections | TK-2821089 | Henry Brandenburg |  | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
QLIK Connections | TK-2561621 | Henry Brandenburg |  | 3.5 | 3.5 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
RAG Improvement | TK-2702944 | Gurpreet Kaur |  | 40 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Rebuild Barcode Parser Class | TK-2821131 | Walter Tallent | In Progress | 16 | 0 | Copy Of Data Ingests into UAP - Rebuild of PPI Version | Sprint 269 | UAP-IV-9443
Rebuild Barcode Parser Class | TK-2782080 | Walter Tallent | In Progress | 24 | 4 | Data Ingests into UAP - Rebuild of PPI Version | Sprint 270 | UAP-IV-9443
Release 2: AI Curator job delay alerts | TK-2782784 | Gurpreet Kaur | In Progress | 12 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443
Release 2: Code review updates | TK-2782901 | Gurpreet Kaur | In Progress | 30 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443
Release 2: Create compute, update job name, set schedule | TK-2782897 | Gurpreet Kaur | In Progress | 8 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443
Release 2: Switch to pandas df | TK-2787031 | Gurpreet Kaur | In Progress | 14 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443
Requirement analysis for FDB, AMS, and eFMS datasource (FEA) | TK-2559770 | Martinnus Tjandra | In Progress | 1 | 1 | Data Ingests into UAP: FEA Facility Golden Record Data: General Business Support | Sprint 270 | UAP-IV-9443
Requirement review and analysis | TK-2821122 | Gener Mercado | In Progress | 23 | 0 | Copy Of Data Ingests into UAP - Facility Golden Record to UAP | Sprint 269 | UAP-IV-9443
Requirement review and analysis | TK-2741352 | Gener Mercado | In Progress | 24 | 1 | Data Ingests into UAP - Facility Golden Record to UAP | Sprint 270 | UAP-IV-9443
Research Manifest / Build Timeline | TK-2821132 | Tracey Jacoby | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - Rebuild of PPI Version | Sprint 269 | UAP-IV-9443
Research Manifest / Build Timeline | TK-2782082 | Tracey Jacoby | In Progress | 1 | 1 | Data Ingests into UAP - Rebuild of PPI Version | Sprint 270 | UAP-IV-9443
Review 431 App Service server error for SAL GenAI | TK-2821096 | Thomas Petty | Completed | 2.25 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
Review App service Server error - User getting 400 error with EDH web app | TK-2821097 | Thomas Petty | Completed | 0.25 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
Review Pat Token Expiration | TK-2829644 | Thomas Petty | Completed | 0.5 | 0 | CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443
RPDC - Mode Matrix, NDLL - Ingestion Rules development | TK-2821144 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
RPDC - Mode Matrix, NDLL - Ingestion Rules development | TK-2678856 | Chandrasekhar Malapati | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
RPDC - Mode Matrix, NDLL 07/29 Release Changes Development | TK-2821153 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
RPDC - Mode Matrix, NDLL 07/29 Release Changes Development | TK-2745601 | Chandrasekhar Malapati | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
RPDC - Mode Matrix, NDLL 09/30 Release Changes Development | TK-2821156 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
RPDC - Mode Matrix, NDLL 09/30 Release Changes Development | TK-2798335 | Chandrasekhar Malapati | In Progress | 20 | 20 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
RPDC - NDLL Ingest feed UAP Development | TK-2821143 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
RPDC - NDLL Ingest feed UAP Development | TK-2631372 | Chandrasekhar Malapati | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
RPDC ‘953’ removal | TK-2821155 | Kai Lebert | Completed | 3 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
Setup Das Environments connection to Storage | TK-2821086 | Ravi Bhupatiraju | In Progress | 23 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
Setup Das Environments connection to Storage | TK-2382328 | Ravi Bhupatiraju | In Progress | 7 | 7 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
Setup GitHub UAP-ING Repo | TK-2821092 | Denetta Eager |  | 4 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
Setup GitHup App & Workflow Repos | TK-2815766 | Ahsan Hashmi | In Progress | 1 | 1 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
Setup GitHup UAP-ING App & Workflow Repos | TK-2821095 | Ahsan Hashmi | In Progress | 39 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443
SIT and CAT testing | TK-2821170 | Oretha Domfeh | In Progress | 10 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
SIT and CAT testing | TK-2820049 | Oretha Domfeh | In Progress | 1 | 1 | Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 270 | UAP-IV-9443
Solution Architecture and Design | TK-2520224 | Rumeel Kazi | In Progress | 26 | 26 | Cloud Administration: Role Based Access and Security: Immuta POC - General Product, Project, and Business Support | Sprint 270 | UAP-IV-9443
Solution Architecture of Metadata lifecycle | TK-2694019 | Rumeel Kazi | In Progress | 113 | 113 | CDAO Architecture: Architecture Review and Assessments - Solution Architecture and Design for Wiki/AI based Metadata management | Sprint 270 | UAP-IV-9443
Solutioning | TK-2414275 | Ravi Bhupatiraju | In Progress | 20 | 10 | Cloud Administration: Role Based Access and Security | Sprint 270 | UAP-IV-9443
Solutioning | TK-2414276 | Peermohamed Kajakamaludeen | In Progress | 1 | 1 | Cloud Administration: Role Based Access and Security | Sprint 270 | UAP-IV-9443
Solutioning | TK-2821036 | Steven Stewart | In Progress | 5 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - Data: Create Workflows/Tables Needed for Facility Level Pure Productive | Sprint 269 | UAP-IV-9443
Solutioning | TK-2817931 | Steven Stewart | In Progress | 1 | 1 | CDAO: Network Dashboard - Enhancements - Data: Create Workflows/Tables Needed for Facility Level Pure Productive | Sprint 270 | UAP-IV-9443
Solutioning and Design for role and attribute based access control | TK-2694015 | Rumeel Kazi | In Progress | 20 | 20 | CDAO Architecture: Architecture Review and Assessments - Design and Analysis of role and attribute-based data access for GIR 773 | Sprint 270 | UAP-IV-9443
Sonar Lint and GitHub integration in VS code | TK-2647373 | Vandana Singh | In Progress | 2 | 2 | Postal Wiki: GenAI - Postal Wiki Review App | Sprint 270 | UAP-IV-9443
SPM chat bot codebase and architectural design review | TK-2647148 | Vandana Singh | In Progress | 28 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443
Sprint Administrative Work | TK-2821018 | Denetta Eager | In Progress | 11 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
Sprint Administrative Work | TK-2606996 | Denetta Eager | In Progress | 20 | 7 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
Standardize Repo Settings | TK-2828431 | Ahsan Hashmi | In Progress | 8 | 1 | CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443
Strategy | TK-2821057 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Strategy | TK-2641109 | Yella Vanga | In Progress | 1 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Supply 1 time historical dump to EDW | TK-2776236 | Lucky Winebarger | In Progress | 1 | 1 | Data Ingests into UAP - Fraud Dataset for EDW | Sprint 270 | UAP-IV-9443
Support SAL EDH Workspace connections to EEB GCP | TK-2829642 | Thomas Petty | Completed | 3 | 0 | CDAO: Platform Support: Data Ingests / Interfaces | Sprint 270 | UAP-IV-9443
Tariffs Duties Collection and Package Intercept Meetings | TK-2821019 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
Tariffs Duties Collection and Package Intercept Meetings | TK-2704321 | Jiang Jing Guang | In Progress | 38 | 38 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
Test Case support | TK-2821176 | Vandana Singh | Completed | 6 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
Test Case support | TK-2821166 | Vandana Singh | Completed | 2 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443
Test Case support | TK-2821190 | Vandana Singh | Completed | 2 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443
Test Cases | TK-2756332 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443
Test Configurability Updates | TK-2826521 | Oretha Domfeh | In Progress | 20 | 20 | Postal Wiki: AI Curator Release 2.5 - configurability updates | Sprint 270 | UAP-IV-9443
Test of Workspace User Role | TK-2826844 | Denetta Eager |  | 5 | 2 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
TOP and NDLL TT1702 model changes | TK-2821149 | Archana Wathore | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
TOP and NDLL TT1702 model changes | TK-2731189 | Archana Wathore | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Tracey Jacoby - PTO | TK-2821034 | Tracey Jacoby | In Progress | 16 | 0 | Copy Of CDAO PTO - OOO | Sprint 269 | UAP-IV-9443
Tracey Jacoby - PTO | TK-2735501 | Tracey Jacoby | In Progress | 1 | 1 | CDAO PTO - OOO | Sprint 270 | UAP-IV-9443
Troubleshoot Git Action Issues | TK-2821048 | Ahsan Hashmi | In Progress | 13 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Troubleshoot Git Action Issues | TK-2513784 | Ahsan Hashmi | In Progress | 1 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
troubleshooting | TK-2821052 | Ari Sherman | In Progress | 16 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
troubleshooting | TK-2627472 | Ari Sherman | In Progress | 28 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Troubleshooting | TK-2821055 | Yella Vanga | In Progress | 2 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Troubleshooting | TK-2641081 | Yella Vanga | In Progress | 6 | 6 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Troubleshooting | TK-2821058 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Troubleshooting | TK-2674745 | Dudley Pratt | In Progress | 5 | 5 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
Troubleshooting | TK-2821063 | Jonathan Trodglen | In Progress | 32 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443
Troubleshooting | TK-2791575 | Jonathan Trodglen | In Progress | 32 | 1 | CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443
TRP (DAS) Workspace Databricks Release Support | TK-2821077 | Denetta Eager | In Progress | 7 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443
TRP (DAS) Workspace Databricks Release Support | TK-2606987 | Denetta Eager | In Progress | 10 | 4.5 | CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443
TSLC and Test in SIT and CAT: application performance | TK-2826523 | Oretha Domfeh | In Progress | 20 | 20 | Postal Wiki: AI Curator Release 2.5 - application performance | Sprint 270 | UAP-IV-9443
TSLC and Deployment Support | TK-2807035 | Vandana Singh | Completed | 4 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443
TSLC and deployment support | TK-2821182 | Vandana Singh | Completed | 3.5 | 0 | Copy Of Postal Wiki: AI Curator Validation Job: Defect - Missing DDL - Z | Sprint 269 | UAP-IV-9443
TSLC and deployment support | TK-2821185 | Vandana Singh | Completed | 3.5 | 0 | Copy Of Postal Wiki: Existing Metadata Context Query Defect - Z | Sprint 269 | UAP-IV-9443
TSLC creation and execution (testing) | TK-2821165 | Oretha Domfeh | In Progress | 20 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443
TSLC creation and execution (testing) | TK-2820045 | Oretha Domfeh | In Progress | 1 | 1 | Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 270 | UAP-IV-9443
TSLC Creation and Testing | TK-2821189 | Oretha Domfeh | In Progress | 20 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443
TSLC Creation and Testing | TK-2820046 | Oretha Domfeh | In Progress | 1 | 1 | Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 270 | UAP-IV-9443
TSLC Creations | TK-2821169 | Oretha Domfeh | In Progress | 20 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
TSLC Creations | TK-2820048 | Oretha Domfeh | In Progress | 1 | 1 | Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 270 | UAP-IV-9443
TSLC for deployment 9/25 | TK-2801359 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.2 | Sprint 269 | UAP-IV-9443
TSLC review | TK-2821177 | Vandana Singh | Completed | 3 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443
TSLC review | TK-2821167 | Vandana Singh | Completed | 1 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443
TSLC review | TK-2821191 | Vandana Singh | Completed | 1 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443
TSLC testing | TK-2821184 | Oretha Domfeh | Completed | 2 | 0 | Copy Of Postal Wiki: Existing Metadata Context Query Defect - Z | Sprint 269 | UAP-IV-9443
TSLC testing in SIT and CAT | TK-2820054 | Oretha Domfeh | Completed | 4 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443
TSLC, SIT and CAT testing | TK-2821181 | Oretha Domfeh | Completed | 4 | 0 | Copy Of Postal Wiki: AI Curator Validation Job: Defect - Missing DDL - Z | Sprint 269 | UAP-IV-9443
TT 1687 AMS Model creation | TK-2821148 | Archana Wathore | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
TT 1687 AMS Model creation | TK-2731179 | Archana Wathore | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
TT1694 Additional RPDC changes | TK-2821150 | Archana Wathore | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
TT1694 Additional RPDC changes | TK-2731198 | Archana Wathore | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
UAP - eModeMatrix API Extract Files New Dimension Table Development | TK-2821141 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
UAP - eModeMatrix API Extract Files New Dimension Table Development | TK-2588117 | Chandrasekhar Malapati | In Progress | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
UAP ING initial set up | TK-2821028 | Laheeb Alsarraf |  | 12 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443
UAP ING initial set up | TK-2789683 | Laheeb Alsarraf |  | 40 | 40 | CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443
UAP meetings | TK-2821031 | Laheeb Alsarraf |  | 0 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443
UAP meetings | TK-2792391 | Laheeb Alsarraf |  | 36 | 36 | CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443
UAP-ING Set-Up | TK-2821025 | Kai Lebert | In Progress | 28 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
UAP-ING Set-Up | TK-2820387 | Kai Lebert | In Progress | 10 | 2 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
UAP-ING WebEOR | TK-2821023 | Tracey Jacoby | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443
UAP-ING WebEOR | TK-2792567 | Tracey Jacoby | In Progress | 1 | 1 | CDAO General Business Support | Sprint 270 | UAP-IV-9443
UI DEV | TK-2755979 | Jesse McGhee | In Progress | 15.5 | 15.5 | CDAO: Network Dashboard - Enhancements - UI(z): Improve UI Visualization in Conjunction with GIS Team | Sprint 270 | UAP-IV-9443
UI Dev | TK-2821038 | Jesse McGhee | In Progress | 4 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - PBI & General UI: Update Feedback Email with Configurable Email Addresses | Sprint 269 | UAP-IV-9443
UI Dev | TK-2808562 | Jesse McGhee | Completed | 2 | 0 | CDAO: Network Dashboard - Enhancements - PBI & General UI(z): Update Feedback Email with Configurable Email Addresses | Sprint 270 | UAP-IV-9443
UI Dev | TK-2824498 | Jesse McGhee | Completed | 6 | 0 | CDAO: Network Dashboard - Enhancements – WS/UI(z): Add Executive Command Center Link to Left Hand Panel (Restricted by Ace ID) | Sprint 270 | UAP-IV-9443
UI Dev | TK-2833831 | Jesse McGhee | In Progress | 16 | 12 | CDAO: Network Dashboard - Enhancements - WS/UI(R): Add Filter for Facilities by Machine Type | Sprint 270 | UAP-IV-9443
UI development | TK-2829635 | Jerry Swank | In Progress | 4 | 3 | CDAO: Network Dashboard - Enhancements - PBI & General UI: Improve the Performance/Look of Service Standard/Performance Tables | Sprint 270 | UAP-IV-9443
UI Development | TK-2835688 | Jerry Swank | In Progress | 8 | 0.75 | CDAO: Network Dashboard - Enhancements - WS/UI(R): Add Filter for Facilities by Machine Type | Sprint 270 | UAP-IV-9443
UI Solutioning | TK-2755977 | Jesse McGhee | In Progress | 7 | 7 | CDAO: Network Dashboard - Enhancements - UI(z): Improve UI Visualization in Conjunction with GIS Team | Sprint 270 | UAP-IV-9443
Update Azure Storage Account | TK-2828430 | Ahsan Hashmi | In Progress | 8 | 1 | CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443
Update insert into table operations | TK-2821162 | Gurpreet Kaur | Completed | 8 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443
Update IVPROD & IVCAT Keyvault Secrets | TK-2821076 | Ahsan Hashmi | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 269 | UAP-IV-9443
Update Key vault Secrets | TK-2816151 | Ahsan Hashmi | In Progress | 1 | 1 | CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443
Update SP Secrets | TK-2828433 | Ahsan Hashmi | In Progress | 10 | 1 | CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443
updates to efms table ingests | TK-2821154 | Walter Tallent |  | 15 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443
updates to efms table ingests | TK-2775260 | Walter Tallent |  | 1 | 1 | Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 270 | UAP-IV-9443
Utilization of PE in Databricks | TK-2632777 | Vandana Singh | In Progress | 24 | 24 | GenAI DIF - Method to chunk and embed tabular data in pdf | Sprint 270 | UAP-IV-9443
Validation support | TK-2821183 | Vandana Singh | Completed | 3.5 | 0 | Copy Of Postal Wiki: AI Curator Validation Job: Defect - Missing DDL - Z | Sprint 269 | UAP-IV-9443
Validation Support | TK-2821186 | Vandana Singh | Completed | 3 | 0 | Copy Of Postal Wiki: Existing Metadata Context Query Defect - Z | Sprint 269 | UAP-IV-9443
Validation Support | TK-2820409 | Vandana Singh | Completed | 3.5 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443
Webapp development | TK-2545095 | Jerry Swank | In Progress | 60 | 58.5 | CDAO: Network Dashboard - Enhancements - PBI App – Dashboard: Utilize Power BI API | Sprint 270 | UAP-IV-9443
WS Dev | TK-2825602 | Jerry Swank | Completed | 2.5 | 0 | CDAO: Network Dashboard - Enhancements – WS/UI(z): Add Executive Command Center Link to Left Hand Panel (Restricted by Ace ID) | Sprint 270 | UAP-IV-9443
WS develoment | TK-2829634 | Jerry Swank | In Progress | 15 | 3 | CDAO: Network Dashboard - Enhancements - PBI & General UI: Improve the Performance/Look of Service Standard/Performance Tables | Sprint 270 | UAP-IV-9443
WS development | TK-2834733 | Jerry Swank | In Progress | 22 | 4.25 | CDAO: Network Dashboard - Enhancements - WS/UI(R): Add Filter for Facilities by Machine Type | Sprint 270 | UAP-IV-9443