## Sheet1
Title | ID | Owner | Status | Est. Hours | To Do | Backlog | Sprint | Planning Level | Imported On
access | TK-2821053 | Ari Sherman | In Progress | 2 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
access | TK-2837129 | Ari Sherman | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Access | TK-2821064 | Jonathan Trodglen | In Progress | 1 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Access | TK-2837140 | Jonathan Trodglen | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Add timeit | TK-2821163 | Gurpreet Kaur | In Progress | 16 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Add timeit | TK-2808249 | Gurpreet Kaur | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Ad-hoc | TK-2821051 | Ari Sherman | In Progress | 8 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Ad-hoc | TK-2837127 | Ari Sherman | In Progress | 16 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Ad-hoc | TK-2821056 | Yella Vanga | In Progress | 4 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Ad-hoc | TK-2837132 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Ad-hoc | TK-2821059 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Ad-hoc | TK-2837135 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Ad-Hoc | TK-2821062 | Jonathan Trodglen | In Progress | 46 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Ad-Hoc | TK-2837138 | Jonathan Trodglen | In Progress | 40.5 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Adhoc/Miscellaneous Work | TK-2821060 | Christine Trang Mai | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Adhoc/Miscellaneous Work | TK-2837136 | Christine Trang Mai | In Progress | 10 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Agent Iteration Log Implementation | TK-2694447 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
AI Curator Code Updates | TK-2821168 | Gurpreet Kaur | Completed | 16 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
AI Sandbox Test Coverage | TK-2725844 | Tyler Russin-Mirabito | In Progress | 1 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Analysis | TK-2821109 | Margaret Albiniak | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Analysis | TK-2837188 | Margaret Albiniak | In Progress | 4.5 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
App service Easy Auth/Okta config updates to filter down groups sent in claims | TK-2837179 | Thomas Petty | Completed | 4.5 | 0 | Copy Of CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Azure Data Factory Configuration | TK-2821088 | Henry Brandenburg | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Azure Data Factory Configuration | TK-2837162 | Henry Brandenburg | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Azure Function App support | TK-2821098 | Ravi Bhupatiraju | In Progress | 7 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Azure Function App support | TK-2837169 | Ravi Bhupatiraju | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Azure Production Deployment | TK-2732320 | Tyler Russin-Mirabito | In Progress | 1 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Build frameworks to ingest WebEOR data into bronze and silver layers | TK-2821196 | Tracey Jacoby | In Progress | 72 | 0 | Copy Of UAP - ING Data Ingests - Ingest WebEOR | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Build frameworks to ingest WebEOR data into bronze and silver layers | TK-2837219 | Tracey Jacoby | In Progress | 96 | 0 | Copy Of UAP - ING Data Ingests - Ingest WebEOR | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO General Business Support | TK-2821017 | Kaelynn Koch | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO General Business Support | TK-2837094 | Kaelynn Koch | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO General Support Work | TK-2821013 | Margaret Albiniak | In Progress | 8 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO General Support Work | TK-2837090 | Margaret Albiniak | In Progress | 7.5 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO Power BI Knowledge Share | TK-2821032 | Margaret Albiniak | In Progress | 1 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO Power BI Knowledge Share | TK-2837107 | Margaret Albiniak | In Progress | 1 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO/DAS General Business Support | TK-2821011 | Denetta Eager | In Progress | 27.5 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO/DAS General Business Support | TK-2837089 | Denetta Eager | In Progress | 42 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Access Support | TK-2821042 | Christine Trang Mai | In Progress | 8 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Access Support | TK-2837121 | Christine Trang Mai | In Progress | 9 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Access Support | TK-2821043 | Dudley Pratt | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Access Support | TK-2837122 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Access Support | TK-2837123 | Ahsan Hashmi | In Progress | 9 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Administrative Support | TK-2821066 | Christine Trang Mai | In Progress | 2 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Administrative Support | TK-2837141 | Christine Trang Mai | In Progress | 6 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Cloud Services Support | TK-2837148 | Christine Trang Mai | In Progress | 6 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Deployment Support | TK-2821083 | Christine Trang Mai | In Progress | 1 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Deployment Support | TK-2837157 | Christine Trang Mai | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Infrastructure Support | TK-2821093 | Christine Trang Mai | In Progress | 14 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Infrastructure Support | TK-2837166 | Christine Trang Mai | In Progress | 32 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Infrastructure Support | TK-2821094 | Dudley Pratt | In Progress | 4 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO: Platform Support: Infrastructure Support | TK-2837167 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
CDAO-Platform Support: Security | TK-2821102 | Christine Trang Mai | In Progress | 6 | 0 | Copy Of CDAO: Platform Support: Security | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CDAO-Platform Support: Security | TK-2837177 | Christine Trang Mai | In Progress | 9 | 0 | Copy Of CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
change Domain-column_name-catalog pair | TK-2801358 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.2 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CIO Data Strategy Support and Tech Chat | TK-2821050 | Rumeel Kazi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
CIO Data Strategy Support and Tech Chat | TK-2837126 | Rumeel Kazi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Access Support | TK-2821041 | Yella Vanga | In Progress | 11 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Access Support | TK-2837120 | Yella Vanga | In Progress | 12 | 0 | Copy Of CDAO: Platform Support: Access Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Cost Meeting | TK-2821021 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Cost Meeting | TK-2837098 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Cost Reporting | TK-2821105 | Denetta Eager | In Progress | 18 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Cost Reporting | TK-2837184 | Denetta Eager | In Progress | 17 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Costing Analysis/Monitoring/Reporting | TK-2821103 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Costing Analysis/Monitoring/Reporting | TK-2837182 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Service Support | TK-2821075 | Yella Vanga | In Progress | 32 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Service Support | TK-2837146 | Yella Vanga | In Progress | 47 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Subscription Administrative Work | TK-2821104 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cloud Subscription Administrative Work | TK-2837183 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Cluster Policies | TK-2821087 | Ravi Bhupatiraju | In Progress | 20 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cluster Policies | TK-2837161 | Ravi Bhupatiraju | In Progress | 20 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Code development and testing | TK-2837204 | Gener Mercado | In Progress | 71 | 0 | Copy Of Data Ingests into UAP - Facility Golden Record to UAP | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Coding | TK-2821120 | Kai Lebert | Completed | 24 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Comment Generation: Create compute, set schedule | TK-2788711 | Gurpreet Kaur | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Comment Generation: Flip flags to 'N' if 'Y' in ai_curator_config at the end of job run | TK-2788719 | Gurpreet Kaur |  | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Comment Generation: Job delay alerts | TK-2788688 | Gurpreet Kaur | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Comment Generation: Switch edh context to pandas df | TK-2788715 | Gurpreet Kaur | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Comment Generation: Update the 'DEFAULT_TABLE_FILTER' name to 'UNALLOWED_TABLE' in ai_curator_configs | TK-2788749 | Gurpreet Kaur |  | 0 | 0 | Postal Wiki: AI Curator Release 2.1 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cost Management | TK-2821074 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Cost Management | TK-2837145 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Cost Management | TK-2837144 | Dudley Pratt | In Progress | 10 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
create and populate 3 tables for TOPS lookups | TK-2821151 | Walter Tallent |  | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Create class of metadata generation notebook | TK-2694937 | Vandana Singh | In Progress | 7 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Create different DMLs for table clean-up, PROD runs, including all domains for salprod | TK-2821175 | Vandana Singh | Completed | 6 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
create ingests for new tables from eFMS database | TK-2821152 | Walter Tallent |  | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Create New Job for Databricks Cluster Dependency Scanning | TK-2837180 | Thomas Petty | Completed | 5 | 0 | Copy Of CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Create/Update Cluster Policies | TK-2837171 | Ahsan Hashmi | In Progress | 11 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Curator run with Llama 3 | TK-2836823 | Vandana Singh | Completed | 2 | 0 | Postal Wiki: AI Curator Release 2.5 - configurability updates | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
DAS All Team Meeting | TK-2821015 | Laheeb Alsarraf |  | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
DAS All Team Meeting | TK-2837092 | Laheeb Alsarraf |  | 0 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
DAS Deployment Support | TK-2821085 | Ravi Bhupatiraju | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
DAS Deployment Support | TK-2837159 | Ravi Bhupatiraju | In Progress | 20 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
DAS Platform Support | TK-2821090 | Henry Brandenburg |  | 33.5 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
DAS Platform Support | TK-2837164 | Henry Brandenburg |  | 58 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Dashborad for metadata coverage | TK-2837217 | Vandana Singh | In Progress | 6 | 0 | Copy Of Postal Wiki: Column descriptions analysis and coverage | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Data Analysis & Team Tracker changes updates | TK-2821125 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Data Analysis & Team Tracker changes updates | TK-2837206 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Collaboration | TK-2821065 | Denetta Eager | In Progress | 2.5 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Lunch & Learn Series | TK-2821027 | Margaret Albiniak | Completed | 0 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Tagging Analysis | TK-2821106 | Denetta Eager | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Tagging Analysis | TK-2837185 | Denetta Eager | In Progress | 2.5 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Tagging for Cost Analysis | TK-2821107 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Tagging for Cost Analysis | TK-2837186 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Tagging support | TK-2837176 | Thomas Petty | Completed | 0.5 | 0 | Copy Of CDAO: Platform Support: Reporting Platform Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Worfklow / Job Support | TK-2821080 | Denetta Eager | In Progress | 5.5 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Databricks Worfklow / Job Support | TK-2837154 | Denetta Eager | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
DDL and DML for ai_curator_acronym | TK-2821172 | Vandana Singh | Completed | 0 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
DDL and DML for ai_curator_glossary | TK-2821171 | Vandana Singh | Completed | 5 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Debugging for test | TK-2836825 | Vandana Singh | Completed | 5 | 0 | Postal Wiki: AI Curator Release 2.5 - configurability updates | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Denetta Eager PTO | TK-2837110 | Denetta Eager | Completed | 2 | 0 | Copy Of CDAO PTO - OOO | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Deployment Support | TK-2821079 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Deployment Support | TK-2837153 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
deployments | TK-2821078 | Ari Sherman | In Progress | 6 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
deployments | TK-2837152 | Ari Sherman | In Progress | 4 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Deployments | TK-2821081 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Deployments | TK-2837155 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Deployments | TK-2821082 | Jonathan Trodglen | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Deployments | TK-2837156 | Jonathan Trodglen | In Progress | 1.5 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Design and development | TK-2821123 | Gener Mercado | In Progress | 55 | 0 | Copy Of Data Ingests into UAP - Facility Golden Record to UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2821113 | Michael Li |  | 39 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2837194 | Michael Li |  | 36 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2821114 | Raheel Aidrus | In Progress | 16 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2837195 | Raheel Aidrus | In Progress | 12 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2821118 | Andrew Toy | In Progress | 0 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2837199 | Andrew Toy | In Progress | 0 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2821111 | Michael Li |  | 0 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2837192 | Michael Li |  | 0 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2821112 | Raheel Aidrus | In Progress | 2 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development | TK-2837193 | Raheel Aidrus | In Progress | 0 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
development | TK-2821037 | Steven Stewart | In Progress | 0 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - Data: Create Workflows/Tables Needed for Facility Level Pure Productive | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development and Deployment | TK-2821135 | Raheel Aidrus | In Progress | 8 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FEA Facility Data API | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development and Deployment | TK-2837215 | Raheel Aidrus | In Progress | 4 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FEA Facility Data API | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Development and Deployment | TK-2821133 | Raheel Aidrus | In Progress | 8 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FAST API | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development and Deployment | TK-2837213 | Raheel Aidrus | In Progress | 6 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FAST API | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Development and Deployment of API for File Upload | TK-2821139 | Raheel Aidrus | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development and Meetings | TK-2821116 | Bryan Stetson | In Progress | 0 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development and Meetings | TK-2837197 | Bryan Stetson | In Progress | 10 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Development and Testing | TK-2821136 | Andrew Toy | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FEA Facility Data API | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development and Testing | TK-2837216 | Andrew Toy | In Progress | 7 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FEA Facility Data API | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Development and Testing | TK-2821134 | Andrew Toy | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FAST API | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Development and Testing | TK-2837214 | Andrew Toy | In Progress | 11.5 | 0 | Copy Of Data Ingests into UAP: DAS API Development - FAST API | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
DML for ai_generated_comment table | TK-2820410 | Vandana Singh | Completed | 3 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
DML for fixing existing run_id | TK-2821187 | Gurpreet Kaur | Completed | 4 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
EDH Deployment Support | TK-2821084 | Ahsan Hashmi | In Progress | 24 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
EDH Deployment Support | TK-2837158 | Ahsan Hashmi | In Progress | 15 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
EDH PROD Support | TK-2821099 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
EDH PROD Support | TK-2837172 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
EDH view, ai_comments, innovation squad assets comparison | TK-2821178 | Vandana Singh | Completed | 3 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Efms TT1689 Additional tables | TK-2821147 | Archana Wathore | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
EIRs for UAP Solution Architecture Support | TK-2821049 | Rumeel Kazi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
EIRs for UAP Solution Architecture Support | TK-2837125 | Rumeel Kazi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Email Validation Workflow | TK-2756329 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
eModeMatrix - DMCR & TT1605 model changes analysis | TK-2821140 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Evaluate TOPS and NDLL data for ingestion | TK-2821138 | Joseph Martinez | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Experiment with domain def. run for logistics domain | TK-2836824 | Vandana Singh | Completed | 6 | 0 | Postal Wiki: AI Curator Release 2.5 - configurability updates | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
FAST - DS, OE files Data Ingest for new 3 column changes | TK-2821121 | Chandrasekhar Malapati | In Progress | 3 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
FAST - DS, OE files Data Ingest for new 3 column changes | TK-2837200 | Chandrasekhar Malapati | In Progress | 4 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
FAST Dev Team Support | TK-2837202 | Kai Lebert | In Progress | 15 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
FDB Feed for UAP using FDB Web Services | TK-2837210 | Robert Bradsher | In Progress | 20 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: FDB Data Feed | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
FEA- Ingest Unit, system Testing | TK-2837209 | Chandrasekhar Malapati | In Progress | 20 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
FEA-AMS Feed Development | TK-2821124 | Chandrasekhar Malapati | In Progress | 13 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
FEA-AMS Feed Development | TK-2837205 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
FEA-EFMS Development | TK-2821126 | Chandrasekhar Malapati | In Progress | 16 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
FEA-EFMS Development | TK-2837207 | Chandrasekhar Malapati | In Progress | 26 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
FEA-FNCM Feed Analysis | TK-2821127 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
FEA-FNCM Feed Analysis | TK-2837208 | Chandrasekhar Malapati | In Progress | 2 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: AMS Data Feed | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Functional architect and data sme | TK-2694933 | Kaelynn Koch | In Progress | 1 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
General Meeting and Solutions | TK-2821024 | Jiang Jing Guang | In Progress | 2.5 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
General Meeting and Solutions | TK-2837101 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
generate comments and test SPM tables in lower environment | TK-2807033 | Vandana Singh | In Progress | 4 | 0 | Postal Wiki: AI Curator Release 2.2 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
GitHub Copilot | TK-2821022 | Kai Lebert | In Progress | 4 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
GitHub Copilot | TK-2837099 | Kai Lebert | In Progress | 9 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
GitHub CoPilot Onboarding and Training / Prompt Engineering | TK-2821029 | Michael Tran | In Progress | 2 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
GitHub CoPilot Onboarding and Training / Prompt Engineering | TK-2837104 | Michael Tran | In Progress | 2 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
GitHub CoPilot Onboarding and Training / Prompt Engineering | TK-2821030 | Denetta Eager | In Progress | 0.5 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
GitHub CoPilot Onboarding and Training / Prompt Engineering | TK-2837105 | Denetta Eager | In Progress | 0 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Graph Creation Tool | TK-2749769 | Tyler Russin-Mirabito | In Progress | 40 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
HR Modernization Meetings | TK-2821020 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
HR Modernization Meetings | TK-2837097 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Implement Logs in SPM code | TK-2669712 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
import data from edw (PPS) | TK-2821145 | Walter Tallent | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Improve logging | TK-2821164 | Gurpreet Kaur | Completed | 4 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Improvements to SQL RAG Feature | TK-2821117 | Bryan Stetson | In Progress | 0 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Improvements to SQL RAG Feature | TK-2837198 | Bryan Stetson | In Progress | 10 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Infrastructure Support | TK-2821091 | Yella Vanga | In Progress | 31 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Infrastructure Support | TK-2837165 | Yella Vanga | In Progress | 37 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
ingest nassweb aft file into databricks | TK-2821129 | Walter Tallent |  | 23 | 0 | Copy Of Data Ingests into UAP - FEA to UAP: NASSWEB Data Feed | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
ingest properties kafka topic | TK-2821197 | Walter Tallent |  | 12 | 0 | Copy Of UAP-ING Data Ingests - Ingeset IPME data for Properties | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
ingest properties kafka topic | TK-2837221 | Walter Tallent |  | 35 | 0 | Copy Of UAP-ING Data Ingests - Ingeset IPME data for Properties | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Integration | TK-2821054 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Integration | TK-2837130 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Integration Help for Client Apps | TK-2821115 | Raheel Aidrus | In Progress | 6 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Integration Help for Client Apps | TK-2837196 | Raheel Aidrus | In Progress | 9 | 0 | Copy Of Conversation Chat: Paisley API - EDL Changes | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Investigate and fix domain_prompt_config table in DEV | TK-2821174 | Vandana Singh | Completed | 2 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Investigate and update edh_bronze.metadata_asset_attribute_description table in SIT | TK-2820411 | Vandana Singh | Completed | 5.5 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Investigate data glossary issue in SIT | TK-2821173 | Vandana Singh | Completed | 2 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Kafka EEB setup | TK-2821014 | Ravi Bhupatiraju |  | 20 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Kafka EEB setup | TK-2837091 | Ravi Bhupatiraju |  | 40 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Kai - OOO | TK-2821035 | Kai Lebert | Completed | 7 | 0 | Copy Of CDAO PTO - OOO | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Kai Lebert | TK-2837109 | Kai Lebert | Completed | 12 | 0 | Copy Of CDAO PTO - OOO | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
make changes to TOPS schema | TK-2821146 | Walter Tallent |  | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Meetings | TK-2821108 | Margaret Albiniak | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Meetings | TK-2837187 | Margaret Albiniak | In Progress | 0 | 0 | Copy Of Cloud Administration - General Project, Product, Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Meetings | TK-2821110 | Bryan Stetson |  | 1 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Meetings | TK-2837191 | Bryan Stetson |  | 3 | 0 | Copy Of Conversation Chat: DCS/MPE Integration | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Meetings | TK-2837220 | Margaret Albiniak | In Progress | 1 | 0 | Copy Of UAP-ING Data Ingests - General Project, Program, Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Meetings (Team 06 Dev & Infrastructure) | TK-2821016 | Kai Lebert | In Progress | 11 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Meetings (Team 06 Dev & Infrastructure) | TK-2837093 | Kai Lebert | In Progress | 5 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
meetings, research initial coding of efms ingest | TK-2821142 | Walter Tallent |  | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Meetings/Functional Support/Investigations | TK-2821039 | Charles Gorelik | In Progress | 33.5 | 0 | Copy Of CDAO: Network Dashboard - Functional and Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Meetings/Functional Support/Investigations | TK-2837118 | Charles Gorelik | In Progress | 39 | 0 | Copy Of CDAO: Network Dashboard - Functional and Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Metadata File Upload App: Set up database | TK-2675244 | Gurpreet Kaur |  | 8 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Metadata File Upload App: Set up Microsoft OAuth | TK-2675246 | Gurpreet Kaur |  | 24 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Metadata File Upload App: Set up Routes | TK-2675197 | Gurpreet Kaur |  | 40 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Metadata File Upload App: Start application | TK-2675196 | Gurpreet Kaur |  | 8 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Network Analytical Dashboard | TK-2821040 | Kevin Nerio | Completed | 80 | 0 | Copy Of CDAO: Network Dashboard - Functional and Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
New appointment_dtm column | TK-2837201 | Kai Lebert | In Progress | 30 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
New Task | TK-2821188 | Gurpreet Kaur | Completed | 4 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Palantir Support | TK-2821067 | Dudley Pratt | In Progress | 5 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Palantir Support | TK-2837142 | Dudley Pratt | In Progress | 15 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Planning, Meetings, Architecture, Sample Files | TK-2821119 | Kai Lebert | Completed | 2 | 0 | Copy Of Data Ingests - Package Payment Scoring PPS EIR 9444: 4 new Attributes to FAST Flat File Load | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Platform Support Team Meetings | TK-2821061 | Denetta Eager | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Platform Support Team Meetings | TK-2837137 | Denetta Eager | In Progress | 2 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Power BI / Rest API Development | TK-2837114 | Kevin Nerio | Completed | 40 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - PBI App – Dashboard: Utilize Power BI API | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Processing CPCTY & UTLZ Investigation | TK-2837119 | Kevin Nerio | Completed | 40 | 0 | Copy Of CDAO: Network Dashboard - Functional and Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Production Support | TK-2821100 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Production Support | TK-2837173 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Production Support | TK-2837175 | Ahsan Hashmi | In Progress | 7 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Production Support DAS and FAST | TK-2821101 | Ravi Bhupatiraju | In Progress | 10 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Production Support DAS and FAST | TK-2837174 | Ravi Bhupatiraju | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Production Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Prototype 1.0 creation | TK-2666326 | Vandana Singh | In Progress | 12 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
QLIK Connections | TK-2821089 | Henry Brandenburg |  | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
QLIK Connections | TK-2837163 | Henry Brandenburg |  | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
RAG Improvement | TK-2702944 | Gurpreet Kaur |  | 40 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Rebuild Barcode Parser Class | TK-2821131 | Walter Tallent | In Progress | 16 | 0 | Copy Of Data Ingests into UAP - Rebuild of PPI Version | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Rebuild Barcode Parser Class | TK-2837211 | Walter Tallent | In Progress | 26 | 0 | Copy Of Data Ingests into UAP - Rebuild of PPI Version | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Release 2: AI Curator job delay alerts | TK-2782784 | Gurpreet Kaur | In Progress | 12 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Release 2: Code review updates | TK-2782901 | Gurpreet Kaur | In Progress | 30 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Release 2: Create compute, update job name, set schedule | TK-2782897 | Gurpreet Kaur | In Progress | 8 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Release 2: Switch to pandas df | TK-2787031 | Gurpreet Kaur | In Progress | 14 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Requirement review and analysis | TK-2821122 | Gener Mercado | In Progress | 23 | 0 | Copy Of Data Ingests into UAP - Facility Golden Record to UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Requirement review and analysis | TK-2837203 | Gener Mercado | In Progress | 23 | 0 | Copy Of Data Ingests into UAP - Facility Golden Record to UAP | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Research Manifest / Build Timeline | TK-2821132 | Tracey Jacoby | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - Rebuild of PPI Version | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Research Manifest / Build Timeline | TK-2837212 | Tracey Jacoby | In Progress | 0 | 0 | Copy Of Data Ingests into UAP - Rebuild of PPI Version | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Review 431 App Service server error for SAL GenAI | TK-2821096 | Thomas Petty | Completed | 2.25 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Review App service Server error - User getting 400 error with EDH web app | TK-2821097 | Thomas Petty | Completed | 0.25 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Review Pat Token Expiration | TK-2837181 | Thomas Petty | Completed | 0.5 | 0 | Copy Of CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
RPDC - Mode Matrix, NDLL - Ingestion Rules development | TK-2821144 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
RPDC - Mode Matrix, NDLL 07/29 Release Changes Development | TK-2821153 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
RPDC - Mode Matrix, NDLL 09/30 Release Changes Development | TK-2821156 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
RPDC - NDLL Ingest feed UAP Development | TK-2821143 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
RPDC ‘953’ removal | TK-2821155 | Kai Lebert | Completed | 3 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Setup Das Environments connection to Storage | TK-2821086 | Ravi Bhupatiraju | In Progress | 23 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Setup Das Environments connection to Storage | TK-2837160 | Ravi Bhupatiraju | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Setup GitHub UAP-ING Repo | TK-2821092 | Denetta Eager |  | 4 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Setup GitHup App & Workflow Repos | TK-2837168 | Ahsan Hashmi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Setup GitHup UAP-ING App & Workflow Repos | TK-2821095 | Ahsan Hashmi | In Progress | 39 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
SIT and CAT testing | TK-2821170 | Oretha Domfeh | In Progress | 10 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
SIT and CAT testing | TK-2820049 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Solution diagram flow and slides | TK-2837218 | Vandana Singh | Completed | 19 | 0 | Copy Of Postal Wiki: Column descriptions analysis and coverage | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Solutioning | TK-2837189 | Ravi Bhupatiraju | In Progress | 10 | 0 | Copy Of Cloud Administration: Role Based Access and Security | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Solutioning | TK-2837190 | Peermohamed Kajakamaludeen | In Progress | 0 | 0 | Copy Of Cloud Administration: Role Based Access and Security | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Solutioning | TK-2821036 | Steven Stewart | In Progress | 5 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - Data: Create Workflows/Tables Needed for Facility Level Pure Productive | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
SPM chat bot codebase and architectural design review | TK-2647148 | Vandana Singh | In Progress | 28 | 0 | Postal Wiki: GenAI - Conversational AI app | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Sprint Administrative Work | TK-2821018 | Denetta Eager | In Progress | 11 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Sprint Administrative Work | TK-2837095 | Denetta Eager | In Progress | 14 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Standardize Repo Settings | TK-2837170 | Ahsan Hashmi | In Progress | 7 | 0 | Copy Of CDAO: Platform Support: Infrastructure Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Strategy | TK-2821057 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Strategy | TK-2837133 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Support SAL EDH Workspace connections to EEB GCP | TK-2837150 | Thomas Petty | Completed | 3 | 0 | Copy Of CDAO: Platform Support: Data Ingests / Interfaces | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Tariffs Duties Collection and Package Intercept Meetings | TK-2821019 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Tariffs Duties Collection and Package Intercept Meetings | TK-2837096 | Jiang Jing Guang | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Test and TSLC support and review | TK-2836826 | Vandana Singh | Completed | 13 | 0 | Postal Wiki: AI Curator Release 2.5 - configurability updates | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Test and TSLC support and review | TK-2836827 | Vandana Singh | Completed | 4 | 0 | Postal Wiki: AI Curator Release 2.5 - application performance | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Test Case support | TK-2821176 | Vandana Singh | Completed | 6 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Test Case support | TK-2821166 | Vandana Singh | Completed | 2 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Test Case support | TK-2821190 | Vandana Singh | Completed | 2 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Test Cases | TK-2756332 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: GenAI - Enabled Intelligent Metadata Generation | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Test Configurability Updates | TK-2826521 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.5 - configurability updates | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Test of Workspace User Role | TK-2837143 | Denetta Eager |  | 3 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
TOP and NDLL TT1702 model changes | TK-2821149 | Archana Wathore | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Tracey Jacoby - PTO | TK-2821034 | Tracey Jacoby | In Progress | 16 | 0 | Copy Of CDAO PTO - OOO | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Tracey Jacoby - PTO | TK-2837108 | Tracey Jacoby | In Progress | 0 | 0 | Copy Of CDAO PTO - OOO | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Troubleshoot Git Action Issues | TK-2821048 | Ahsan Hashmi | In Progress | 13 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Troubleshoot Git Action Issues | TK-2837124 | Ahsan Hashmi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
troubleshooting | TK-2821052 | Ari Sherman | In Progress | 16 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
troubleshooting | TK-2837128 | Ari Sherman | In Progress | 20 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Troubleshooting | TK-2821055 | Yella Vanga | In Progress | 2 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Troubleshooting | TK-2837131 | Yella Vanga | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Troubleshooting | TK-2821058 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Troubleshooting | TK-2837134 | Dudley Pratt | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Troubleshooting | TK-2821063 | Jonathan Trodglen | In Progress | 32 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Troubleshooting | TK-2837139 | Jonathan Trodglen | In Progress | 35 | 0 | Copy Of CDAO: Platform Support: Administrative Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
TRP (DAS) Workspace Databricks Release Support | TK-2821077 | Denetta Eager | In Progress | 7 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TRP (DAS) Workspace Databricks Release Support | TK-2837151 | Denetta Eager | In Progress | 5.5 | 0 | Copy Of CDAO: Platform Support: Deployment Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
TSLC and Test in SIT and CAT: application performance | TK-2826523 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.5 - application performance | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
TSLC and Deployment Support | TK-2807035 | Vandana Singh | Completed | 4 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC and deployment support | TK-2821182 | Vandana Singh | Completed | 3.5 | 0 | Copy Of Postal Wiki: AI Curator Validation Job: Defect - Missing DDL - Z | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC and deployment support | TK-2821185 | Vandana Singh | Completed | 3.5 | 0 | Copy Of Postal Wiki: Existing Metadata Context Query Defect - Z | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC creation and execution (testing) | TK-2821165 | Oretha Domfeh | In Progress | 20 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC creation and execution (testing) | TK-2820045 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
TSLC Creation and Testing | TK-2821189 | Oretha Domfeh | In Progress | 20 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC Creations | TK-2821169 | Oretha Domfeh | In Progress | 20 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC Creations | TK-2820048 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
TSLC for deployment 9/25 | TK-2801359 | Oretha Domfeh | In Progress | 0 | 0 | Postal Wiki: AI Curator Release 2.2 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC review | TK-2821177 | Vandana Singh | Completed | 3 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - Domain-Configurable Glossary and Acronym Reference Tables for Quality Metadata | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC review | TK-2821167 | Vandana Singh | Completed | 1 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC review | TK-2821191 | Vandana Singh | Completed | 1 | 0 | Copy Of Postal Wiki: RunID Auto-increment Fails After Value 9 Defect | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC testing | TK-2821184 | Oretha Domfeh | Completed | 2 | 0 | Copy Of Postal Wiki: Existing Metadata Context Query Defect - Z | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC testing in SIT and CAT | TK-2820054 | Oretha Domfeh | Completed | 4 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TSLC, SIT and CAT testing | TK-2821181 | Oretha Domfeh | Completed | 4 | 0 | Copy Of Postal Wiki: AI Curator Validation Job: Defect - Missing DDL - Z | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TT 1687 AMS Model creation | TK-2821148 | Archana Wathore | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
TT1694 Additional RPDC changes | TK-2821150 | Archana Wathore | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
UAP - eModeMatrix API Extract Files New Dimension Table Development | TK-2821141 | Chandrasekhar Malapati | In Progress | 0 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
UAP ING initial set up | TK-2821028 | Laheeb Alsarraf |  | 12 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
UAP ING initial set up | TK-2837103 | Laheeb Alsarraf |  | 1 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UAP meetings | TK-2821031 | Laheeb Alsarraf |  | 0 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
UAP meetings | TK-2837106 | Laheeb Alsarraf |  | 1 | 0 | Copy Of CDAO Non-Project Work - Training | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UAP-ING Set-Up | TK-2821025 | Kai Lebert | In Progress | 28 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
UAP-ING Set-Up | TK-2837102 | Kai Lebert | In Progress | 8 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UAP-ING WebEOR | TK-2821023 | Tracey Jacoby | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
UAP-ING WebEOR | TK-2837100 | Tracey Jacoby | In Progress | 0 | 0 | Copy Of CDAO General Business Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UI DEV | TK-2755979 | Jesse McGhee | In Progress | 0 | 0 | CDAO: Network Dashboard - Enhancements - UI(z): Improve UI Visualization in Conjunction with GIS Team | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UI Dev | TK-2821038 | Jesse McGhee | In Progress | 4 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - PBI & General UI: Update Feedback Email with Configurable Email Addresses | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
UI Dev | TK-2808562 | Jesse McGhee | Completed | 2 | 0 | CDAO: Network Dashboard - Enhancements - PBI & General UI(z): Update Feedback Email with Configurable Email Addresses | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UI Dev | TK-2824498 | Jesse McGhee | Completed | 6 | 0 | CDAO: Network Dashboard - Enhancements – WS/UI(z): Add Executive Command Center Link to Left Hand Panel (Restricted by Ace ID) | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UI Dev | TK-2837115 | Jesse McGhee | In Progress | 4 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - WS/UI(R): Add Filter for Facilities by Machine Type | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UI Development | TK-2444807 | Jerry Swank |  | 0 | 0 | CDAO: Network Dashboard - Enhancements(z) - General UI changes - Update Business legend to filter by Annualized Revenue | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UI development | TK-2837112 | Jerry Swank | In Progress | 1 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - PBI & General UI: Improve the Performance/Look of Service Standard/Performance Tables | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UI Development | TK-2837117 | Jerry Swank | In Progress | 7.25 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - WS/UI(R): Add Filter for Facilities by Machine Type | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
UI Solutioning | TK-2755977 | Jesse McGhee | In Progress | 0 | 0 | CDAO: Network Dashboard - Enhancements - UI(z): Improve UI Visualization in Conjunction with GIS Team | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Update Azure Storage Account | TK-2837149 | Ahsan Hashmi | In Progress | 7 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Update insert into table operations | TK-2821162 | Gurpreet Kaur | Completed | 8 | 0 | Copy Of Postal Wiki: AI Curator Release 2.4 - application performance | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Update IVPROD & IVCAT Keyvault Secrets | TK-2821076 | Ahsan Hashmi | In Progress | 3 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Update Key vault Secrets | TK-2837147 | Ahsan Hashmi | In Progress | 0 | 0 | Copy Of CDAO: Platform Support: Cloud Services Support | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Update planner, create story | TK-2836828 | Vandana Singh | Completed | 2 | 0 | Postal Wiki: AI Curator Release 2.5 - application performance | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Update planner, create story, admin tasks | TK-2836829 | Vandana Singh | Completed | 3 | 0 | Postal Wiki: AI Curator Release 2.5 - configurability updates | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Update SP Secrets | TK-2837178 | Ahsan Hashmi | In Progress | 9 | 0 | Copy Of CDAO: Platform Support: Security | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
updates to efms table ingests | TK-2821154 | Walter Tallent |  | 15 | 0 | Copy Of Data Ingests into UAP: RPDC/LDC/LPDC Load into UAP | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Validation support | TK-2821183 | Vandana Singh | Completed | 3.5 | 0 | Copy Of Postal Wiki: AI Curator Validation Job: Defect - Missing DDL - Z | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Validation Support | TK-2821186 | Vandana Singh | Completed | 3 | 0 | Copy Of Postal Wiki: Existing Metadata Context Query Defect - Z | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Validation Support | TK-2820409 | Vandana Singh | Completed | 3.5 | 0 | Postal Wiki: AI Curator Release 2.3 | Sprint 269 | UAP-IV-9443 | 2025-11-04 08:55
Webapp development | TK-2837113 | Jerry Swank | In Progress | 1.5 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - PBI App – Dashboard: Utilize Power BI API | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
Webapp development | TK-2545114 | Jerry Swank |  | 0 | 0 | CDAO: Network Dashboard - Enhancements(z) - UI: Add Saved Selection Functionality | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
WS Dev | TK-2825602 | Jerry Swank | Completed | 2.5 | 0 | CDAO: Network Dashboard - Enhancements – WS/UI(z): Add Executive Command Center Link to Left Hand Panel (Restricted by Ace ID) | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
WS develoment | TK-2837111 | Jerry Swank | In Progress | 12 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - PBI & General UI: Improve the Performance/Look of Service Standard/Performance Tables | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55
WS development | TK-2837116 | Jerry Swank | In Progress | 17.75 | 0 | Copy Of CDAO: Network Dashboard - Enhancements - WS/UI(R): Add Filter for Facilities by Machine Type | Sprint 270 | UAP-IV-9443 | 2025-11-04 08:55